## Project Plan
Functionality | Active/ Completed | Duration in days (Estimate) | Days remaining | Start Date | End Date | Duration in days (Actual) | Dependancy | Notes
Map needs to be draggable and marker needs to be always in centre | Completed | 0.2
As the customer drags the map, if the distance between old and new marker position is >=20m then request ‘nearest driver’ again | Completed | ?
The webservice returns driver’s driving distance from the pickup location in minutes | Completed | 0.4
The time needs to be displayed inside the marker as per design. | Completed | 0.2
When you request ‘nearest driver’ you need to reverse geocode the new location again at the same time and display the new pickup address in the pickup textbox | Completed | 0.4
The pickup and dropoff address textbox both need two taps before the keypad opens up. Please check the issue | Completed | 0.1
Limit the frequently used address to maximum 5. | Completed | 0.1
As soon as both addresses are available quotation needs to requested and displayed. | Completed | 0.2
The quotation needs to be invalidated as soon as any of the address changes. | Completed | 0.2
If the customer clicks the ‘+’ button next to the dropoff address then a new textbox needs to be appended below it. It will be called ‘via address’ | Completed | 0.2
With any address/datetime changes the quotation needs to be recalled | Completed | 0.2
On ‘confirm booking’ button click the app crashes CTR+SHIFT+T | Completed | 1
This menu needs to be on top of the textboxes on the bottom of the page | Completed | 0.2
‘Current bookings’, ‘Booking History’ and ‘Profile’ needs to be kept hidden until the customer logs in |  | 0.2
If there are no bookings/history then the customer needs to be prompted and brought back to the main screen |  | 0.5

## Issues log
Issue # | Name | Description | Date entered | Plan to resove / Activity | Date closed