## Project Plan
Functionality | Active/ Completed | Duration in days (Estimate) | Days remaining | Start Date | End Date | Duration in days (Actual) | Dependancy | Notes
Map needs to be draggable and marker needs to be always in centre | Completed | 0.2
As the customer drags the map, if the distance between old and new marker position is >=20m then request ‘nearest driver’ again | Completed | ?
The webservice returns driver’s driving distance from the pickup location in minutes | Completed | 0.4
The time needs to be displayed inside the marker as per design. | Completed | 0.2
When you request ‘nearest driver’ you need to reverse geocode the new location again at the same time and display the new pickup address in the pickup textbox | Completed | 0.4
The pickup and dropoff address textbox both need two taps before the keypad opens up. Please check the issue | Completed | 0.1
Limit the frequently used address to maximum 5. | Completed | 0.1
As soon as both addresses are available quotation needs to requested and displayed. | Completed | 0.2
The quotation needs to be invalidated as soon as any of the address changes. | Completed | 0.2
If the customer clicks the ‘+’ button next to the dropoff address then a new textbox needs to be appended below it. It will be called ‘via address’ | Completed | 0.2
With any address/datetime changes the quotation needs to be recalled | Completed | 0.2
On ‘confirm booking’ button click the app crashes CTR+SHIFT+T | Completed | 1
This menu needs to be on top of the textboxes on the bottom of the page | Completed | 0.2
‘Current bookings’, ‘Booking History’ and ‘Profile’ needs to be kept hidden until the customer logs in |  | 0.2
Custom client location marker like a point and don't show "You here". We not going to track them.
move search textbox into the tool bar in GetAddressActivity
Add Nearly into listview in GetAddressActivity just like "Home" and "Frequent"
Add login option in menu bar whenever the customer not login yet
check functions SaveBooking! It's not work correctly
If there are no bookings/history then the customer needs to be prompted and brought back to the main screen |  | 0.5

## Issues log
Issue # | Name | Description | Date entered | Plan to resove / Activity | Date closed